## Meetings
Meeting Date | Action | Responsible | Update | Status
12.6.2023 | LD to approach CLA with an invitation to be a landowner representative on the LNRS Steering Group. | LD |  | Ongoing
12.6.2023 | LD to brief Farm Herefordshire on the decision. | LD |  | Ongoing
12.6.2023 | FL to share the wire diagram being developed within HC showing the various existing partnerships and how they relate to one another. | FL | FL Provided the wire frame diagram by email 21/6/2023 | Completed
12.6.2023 | FL to amend the draft Terms of Reference and recirculate prior to the next meeting. | FL | FL had amended the draft, sought comments from NE and will circulate an amended draft ToR with the minutes of the 11/7/2023 meeting. These can be revisited again in future meetings. | Ongoing
12.6.2023 | Herefordshire Council to meet with HWT to view HWT/GWT mapping work and understand whether it meets the requirements of the Regulations/Guidance or whether we could work with it going forward and to report back. | HC | FL/LD/EG met with Claire Spicer at HWT to discuss the mapping 19/6/2023. Followed up with a meeting with Juliet Hynes at Gloucestershire Wildlife Trust on 6/7/2023 which informed the mapping proposals document to be considered at the steering group meeting on 11/7/2023. | Completed
12.6.2023 | EG to do an evidence gap analysis around data and report back. | EG | The various meetings around mapping have advanced HC's understanding of mapping requirements and gaps/next steps are set out in the mapping proposals document to be ocnsidered at the steering group meeting on 11/7/2023. | Ongoing
12.6.2023 | LD to contact Nicola Hillary at Gloucestershire LNRS with the hope of learning from their advanced position. | LD | LD and FL had a useful meeting with Nicola Hillary at Gloucestershire LNRS on 30/6/2023. | Completed
12.6.2023 | FL to draft an early engagement questionnaire to bring to the next meeting. | FL | The conversations with various other Responsible Authorities have raised questions about the value of early engagement which require further discussion. This will be an item on the agenda for the September 2023 steering group meeting. | Not started
12.6.2023 | HC to create a basic landing page on the HC website. | HC | Draft text has been created and the process for creating a new webpage on the HC website is underway. NE confirmed that this needs to be launched and provided to defra by end August 2023. Release of this will be co-ordinated with local press on LNRS. | ongoing
12.6.2023 | FL/LD/SB to consider whether parts of the existing HC stakeholder list might be helpful in forming a wide stakeholder list for this work and report back. | FL/LD/SB | Worcestershire have provided their stakeholder list which will also feed into the development of a Herefordshire stakeholder list. | Ongoing
12.6.2023 | HC to draft role/responsibilities of the chair for further discussion at next meeting. | HC |  | Not started
12.6.2023 | FL to continue to work on the timetable to reflect the revised timetable, to break it down into stages and task so that we can start being specific. To bring back to the next meeting. | FL | HC have focussed on advancing the understanding and proposals around mapping this month and suggest that engagement and timetable should be the focus of the September 2023 meeting | Ongoing