## Meeting Dates & Actions
Meeting Date | Action | Responsible | Update | Status
12.6.2023 | LD to approach CLA with an invitation to be a landowner representative on the LNRS Steering Group. | LD | Helen Dale agreed to join SG | Completed
12.6.2023 | LD to brief Farm Herefordshire on the decision. | LD |  | Completed
12.6.2023 | FL to share the wire diagram being developed within HC showing the various existing partnerships and how they relate to one another. | FL | FL Provided the wire frame diagram by email 21/6/2023 | Completed
12.6.2023 | FL to amend the draft Terms of Reference and recirculate prior to the next meeting. | FL | FL had amended the draft, sought comments from NE and will circulate an amended draft ToR with the minutes of the 11/7/2023 meeting. These can be revisited again in future meetings. | Completed
12.6.2023 | Herefordshire Council to meet with HWT to view HWT/GWT mapping work and understand whether it meets the requirements of the Regulations/Guidance or whether we could work with it going forward and to report back. | HC | FL/LD/EG met with Claire Spicer at HWT to discuss the mapping 19/6/2023. Followed up with a meeting with Juliet Hynes at Gloucestershire Wildlife Trust on 6/7/2023 which informed the mapping proposals document to be considered at the steering group meeting on 11/7/2023. | Completed
12.6.2023 | EG to do an evidence gap analysis around data and report back. | EG | The various meetings around mapping have advanced HC's understanding of mapping requirements and gaps/next steps are set out in the mapping proposals document to be considered at the steering group meeting on 11/7/2023. Proposals were considered and approved on 11/7/2023. HC have approached GWT for a formal quote which will be shared once available. The sharing of the quote will be an item on the agenda for 19.10.2023 | Ongoing
12.6.2023 | LD to contact Nicola Hillary at Gloucestershire LNRS with the hope of learning from their advanced position. | LD | LD and FL had a useful meeting with Nicola Hillary at Gloucestershire LNRS on 30/6/2023. | Completed
12.6.2023 | FL to draft an early engagement questionnaire to bring to the next meeting. | FL | The conversations with various other Responsible Authorities have raised questions about the value of early engagement which require further discussion. This will be an item on the agenda for the September 2023 steering group meeting. | Agreed to be reviewed as part of wider engament workshop
12.6.2023 | HC to create a basic landing page on the HC website. | HC | Draft text has been created and the process for creating a new webpage on the HC website is underway. NE confirmed that this needs to be launched and provided to defra by end August 2023. Release of this will be co-ordinated with local press on LNRS. Page went live 8.9.2023 www.herefordshire.gov.uk/lrns | Completed
12.6.2023 | FL/LD/SB to consider whether parts of the existing HC stakeholder list might be helpful in forming a wide stakeholder list for this work and report back. | FL/LD/SB | Worcestershire have provided their stakeholder list which will also feed into the development of a Herefordshire stakeholder list. | Ongoing
12.6.2023 | HC to draft role/responsibilities of the chair for further discussion at next meeting. | HC |  | Currently HC Chairing, will be reviewed as required.
12.6.2023 | FL to continue to work on the timetable to reflect the revised timetable, to break it down into stages and task so that we can start being specific. To bring back to the next meeting. | FL | HC have focussed on advancing the understanding and proposals around mapping this month and suggest that engagement and timetable should be the focus of the September 2023 meeting. Remains ongoing. | Ongoing
18.9.2023 | FL to update job advert to include land based backgrounds rather than solely biodiversity. Once confirmed advert to be publicised. | FL | Done | Completed
18.9.2023 | RP to circulate advert to the LNRS forum. | RP | Done. Closing date is 15.12.23 | Completed
18.9.2023 | FL/JE to update table of members and add that Terms of Reference are subject to periodic review and change | FL/JE | Done | Completed
18.9.2023 | Further discussions/development of engagement should form part of a working group on engagement and consultation | FL | Initial meeting of the engagement group is scheduled for 8.1.24 | Ongoing
18.9.2023 | HC to develop some potential options around task and finish groups for the steering group to discuss at the October meeting. | HC | Initial options presented and discussed in October | Completed
19.10.2023 | HC to proceed with formally procuring the LNRS Mapping from Gloucestershire Wildlife Trust | HC | Consulancy Agreement underway | Ongoing
19.10.2023 | FL to update the draft organisational structure to reflect the discussion at the October Steering Group | FL | An amended partnership structure circulated 18.12.23 along with a request for volunteers/nominations for groups | Ongoing
29.11.2023 | FL to add minutes and relevant papers to the website and update the actions log. | FL |  | Ongoing
29.11.2023 | EG to source and share the data layers to be used in the Gloucestershire Wildlife Trust mapping work with the data working group for info. | EG |  | Target - Jan 24
29.11.2023 | EG to carry out initial work on species list prior to engaging with stakeholders. | EG |  | Target - Jan/Feb 24
29.11.2023 | RP to share info on Worcestershire’s use of ‘Survey 123’ within the next month or so. | RP |  | Target - Jan 24
29.11.2023 | FL to draft rough engagement plan for strategy for early January meetings | FL |  | Ongoing
29.11.2023 | FL to circulate a spreadsheet with a full list of task and finish groups to steering group. | FL |  | Ongoing
29.11.2023 | All to fill in spreadsheet with where they see themselves fitting in and to nominate other relevant organisations/individuals to particular groups. | All |  | Ongoing
29.11.2023 | Engagement task and finish group (FL, RP, EW, HD plus comms reps from HC, AONB and HWT) to meet and draft a set of actions at January meeting. | FL plus others | Meeting 8th January 10.30am | Ongoing
29.11.2023 | FL/EG/LD to pull together an outline tender document for procuring the Strategy element of the work based on the feedback from this SG meeting | FL/LD/EG |  | Target - Jan 24